Invitation to Bid
Davenport Brothers · 455 Sumpter Rd, Van Buren Township, Michigan 48111 · 734-697-2994 · Estimating@davenportbrothers.com
November 9, 2026
	Project information
	

	Project
	West End Rail – Shop Building, Modular Office & Truck Scale (CSX Transflo Detroit)

	Owner
	Crown Enterprises, 12225 Stephens Rd., Warren, MI 48089

	Location
	West End Rail Yard, 8000 Melville Street, Detroit, MI 48209

	Design team
	FormSurfaces Design Group (architectural), Conn Engineering Consultants (structural), Systems Solution Engineering (MEP)

	Building permit
	City of Detroit BLD2026-00154 (issued 09-21-2026, paid by Owner)

	Contract type
	Lump sum, GC bid package


Dear Subcontractor / Supplier,
Davenport Brothers invites your firm to bid the trade work listed below on the West End Rail project in Detroit. The work includes a new 50' x 64' (3,200 SF) pre-engineered metal shop building erected from an Owner-furnished metal building system, complete in all trades. It also includes foundations and utility connections for an Owner-furnished 23'-4" x 60' modular office, the concrete pit foundation for an 80' x 11' truck scale, and adjacent walks, pads, a dumpster enclosure and bollards.
Drawings and Specifications Location: All drawings, specifications and Contract Documents for this project are available for download in the Bid Room – Davenport Brothers Construction. To receive a zip file of the documents instead, email Estimating@davenportbrothers.com.
Bid Dates
Subcontractor bids are due to Davenport Brothers by 12:00 PM on Monday, November 30, 2026.
	Event
	Date and time

	Pre-bid meeting / site walk
	None. Site visits by appointment only; contact Davenport Brothers to arrange.

	Questions / RFIs to Davenport Brothers
	Wednesday, November 18, 2026, 12:00 PM

	Subcontractor bids due to Davenport Brothers
	Monday, November 30, 2026, 12:00 PM

	Davenport Brothers' bid due to Owner
	Thursday, December 3, 2026, 5:00 PM


Email bids to Estimating@davenportbrothers.com with the subject line "West End Rail – [Trade] – [Company Name]." Send questions to the same address; we will forward them to the Owner before the Owner's question deadline of Friday, November 20 at 5:00 PM. Answers will be issued by addendum. Please do not contact the Owner or its separate contractors directly about this bid.
Bid Packages
We are taking bids on the scopes below. Bidders are responsible for the complete Contract Documents, including the permit drawings (G-000 to P-400), civil sheets, scale pit Sheet S1, the modular office State-approved plans, the TEC geotechnical report 65933, and the metal building anchor rod and erection drawings. RFP section references (A1–D1) are in parentheses.
	Bid package
	Scope summary

	Earthwork & Excavation
	Building and scale pit pad earthwork (footprint + 5'), stripping, removal of unsuitable fill, over-excavation (2' min. below footings) and engineered fill per TEC, proof-rolling, foundation backfill, incidental dewatering, excavation support per MIOSHA, legal off-site disposal of spoils, 6" 22A gravel restoration (A1, B1, C1, D1).

	Concrete & Reinforcing
	Formed footings, 8" frost walls, spread footings, piers, anchor rods and leveling plates per the anchor rod plan, non-shrink grout, 8" slab-on-grade with #5 @ 12" e.w. and vapor retarder, R-15 slab-edge insulation, grounding electrode; modular office pier footings; scale pit slab, walls, piers, sumps and deck pour; 6" walks, stoops, aprons and 8" pads; dumpster pad. Ready-mix and aggregate through Hercules Materials Holdings (A2, B1, C1, D1).

	Metal Building Erection
	Receive, unload, inventory and protect the Owner-furnished Metallic Building Systems package (~28,100 lb, Job 21-B-63283); erect framing, bracing, Double-Lok standing seam roof, PBR walls, trims, gutters, downspouts, framed openings and two walk doors (A3).

	Insulation & Liner Panels
	Roof and wall insulation to meet COMcheck, compatible with high clips and thermal blocks; interior liner panels per A-101 / A-502 (A3).

	Steel & Misc. Metals
	Rebar supply, anchor rods (F1554 Gr. 55 at Detail J), L3x3x1/4 scale pit coping (~190 LF), concrete-filled pipe bollards, strut / backing for service equipment, stair / ramp railings (A2, A3, A4, B2, C1).

	Doors, Frames, Hardware & Windows
	Two 12' x 20' insulated overhead doors with operators (3-year warranty on operators), hollow metal doors, frames and hardware, interior doors and windows per A-501 (A4).

	Interiors
	Metal stud and gypsum board partitions (moisture-resistant where scheduled), acoustical ceilings, plywood wainscot, FRP, painting, sealed concrete, resilient base, toilet partitions and accessories, lockers and benches, break room casework, signage, fire extinguishers and cabinets (A4).

	Plumbing
	Underground sanitary, trench drain / catch basin, floor drains, water meter and backflow preventer, fixtures, water heater, gas piping from the DTE meter, 1" water line to the modular office with heat trace, modular sanitary connection, scale pit sump pumps and discharge to the 12" storm stub (A1, A5, B2, C1).

	HVAC
	Furnace and condensing unit, infrared tube heater, ERV, exhaust fans, unit heater, ductwork, controls, CO detection, flues, gas connections, start-up and test & balance; 5-year warranty on HVAC equipment (A5).

	Electrical
	All work from the load side of the service disconnects: feeders to TR-AA, LP-AA, LCP-AA and RP-A, branch circuits, lighting and controls, exit / emergency, equipment connections, telecom backboard and conduits; underground feeders to modular Panels A and B; scale power, data conduits, stop / go pole and grounding (design-build if not detailed by addendum); Alt. 1 fire alarm price (A6, B2, C2).

	Modular Office Foundation Design
	Site-specific foundation and tie-down design sealed by a Michigan PE (2,000 psf max; 3,150 lb min. corner tie-downs), submitted to BSEED (B1).

	Modular Stairs & Ramps
	Code-compliant exterior stairs, landings, handrails and accessible ramp(s) at all modular office doors, on foundations below frost (B2).

	Surveying & Layout
	Licensed surveyor layout of building corners, anchor rods, scale pit and modular piers; as-built survey of underground utilities.

	Dumpster Enclosure
	PVC solid fence enclosure and gates for a 6-yard container per Sheet C2 (D1).


Bids for a single package or for combined packages are welcome. Please price each package separately so we can compare.
Bid Requirements
1. Lump sum price per bid package, including all labor, material, equipment, cranes, hoisting, freight and applicable taxes.
2. Include winter conditions: temporary heat and enclosures, frost protection of subgrades and footings, cold-weather concrete and snow removal in your work areas. No fill or concrete on frozen ground.
3. Include incidental dewatering and excavation support. Groundwater was found 4.8 to 12 ft below grade.
4. Obtain and pay for your trade permits, plan review and inspection fees. The building permit fee is paid by the Owner.
5. Two-year warranty on all workmanship and materials from Substantial Completion; 5 years on HVAC equipment; 3 years on overhead door operators.
6. Insurance per Crown's Rider B, naming Crown Enterprises LLC, Riverview Trenton Railroad Company and affiliates as additional insureds. Railroad Protective Liability is required for work within 50 ft of railroad property.
7. Bonds are not required. Please quote your bond rate separately in case the Owner requests bonds.
8. Provide unit prices where they apply to your trade: undercut and 21AA replacement, Class II sand, soil disposal, special disposal, added foundation concrete, added 6" flatwork, added bollards, and hourly labor rates.
9. Stop work and notify us immediately if suspect contaminated material is encountered (fill at Boring No. 1 had a petroleum-type odor).
10. Coordinate with the Owner's separate site, paving, electrical, rail and fence contractors and with Metallic / NCI, Mobile Modular and Boni Hutchinson.
11. Acknowledge all addenda, list exclusions and qualifications, and keep prices firm for 60 days after December 3, 2026.
12. Include a proposed schedule and your crew duration. Work starts as soon as possible after award.
The Owner's Design Clarifications in the RFP apply; for example, the shop building is 50' x 64' (3,200 SF) and the modular office is 23'-4" x 60'. Bid as clarified unless revised by addendum.
Bid Documents
Crown's RFP – GC Bid Package dated November 8, 2026 (with Exhibits A, B and C) and all Contract Documents listed in it, including Crown's Terms and Conditions rev. 03-14-26.
Plans and specifications: download them from the Bid Room – Davenport Brothers Construction.
Prefer a direct copy? Email Estimating@davenportbrothers.com and we will email you a zip file of the plans and specifications.
Please reply by Wednesday, November 18 to let us know whether you will be bidding. Thank you for your interest; we look forward to your proposal.
Sincerely,
Davenport Brothers
Mark Davenport mark@davenportbrothers.com · 734-697-2994

